## Introduction
PREDICTING LIFE EXPECTANCY USING MACHINE LEARNING PROJECT PLAN
Purpose: A typical Regression Machine Learning project leverages historical data to predict insights into the future. This problem statement is aimed at predicting Life Expectancy rate of a country given various features. Life expectancy is a statistical measure of the average time a human being is expected to live, Life expectancy depends on various factors: Regional variations, Economic Circumstances, Sex Differences, Mental Illnesses, Physical Illnesses, Education, Year of their birth and other demographic factors. This problem statement provides a way to predict average life expectancy of people living in a country when various factors such as year, GDP, education, alcohol intake of people in the country, expenditure on healthcare system and some specific disease related deaths that happened in the country are given.

## Project Plan - Pilot
PREDICTING LIFE EXPECTANCY USING MACHINE LEARNING PROJECT PLAN
[6 empty] | Period Highlight: |  |  |  |  | 1 |  |  |  | Plan |  |  | Actual |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
| PLAN | PLAN | ACTUAL | ACTUAL | PERCENT
ACTIVITY | START | DURATION | START | DURATION | COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Pre-Requisites
Project Planning And Kickoff | 1 | 1 | 1 | 1 | 100%
Creating IBM Cloud Account | 1 | 2 | 1 | 2 | 100%
Installing ML Services and Watson Studio | 2 | 1 | 2 | 1 | 100%
Creating Node Red account | 2 | 1 | 2 | 1 | 100%
Predicting Life Expectancy Using ML
Collect The Dataset For The Project | 2 | 1 | 2 | 1 | 100%
Create Necessary IBM Cloud Services | 3 | 1 | 3 | 1 | 100%
Create A Watson Studio Project | 3 | 1 | 3 | 1 | 100%
Configure Watson Studio | 3 | 1 | 3 | 1 | 100%
Create Machine Learning Service | 4 | 1 | 4 | 1 | 100%
Create A Jupyter Notebook In IBM Watson And Import Data | 4 | 1 | 4 | 1 | 100%
Configure Watson Studio | 4 | 2 | 4 | 2 | 100%
Build a Machine Learning model and create end points for node red integration | 5 | 1 | 5 | 1 | 100%
Build Node red flow to integrate ML services | 5 | 2 | 5 | 2 | 100%
Deploying the model | 6 | 1 | 6 | 1 | 100%
Execute the Program
Deploying the code In ML Watson Studio | 5 | 5 | 5 | 5 | 0%
Using the API keys and executing it on node red | 10 | 6 | 10 | 6 | 0%
Capture Value From Machine Learning
Predicted the Life Expectancy | 10 | 6 | 10 | 6 | 0%
Learnt linear regression | 10 | 6 | 10 | 6 | 0%
Used various softwares like node red and IBM Cloud | 10 | 6 | 10 | 6 | 0%